## excel (5)
/Non Project/PSP Fundamentals & Advanced/Program 7
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Juan Pablo Ospino Solano
Start Date | may 01, 2017 02:54:48 PM
Completion Date | may 03, 2017 10:33:10 PM |  |  |  | Completed: *
Keywords
Language | Java
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 22.5 | 20.4 | 25.6
Planned Time | 0.25903 |  | 1899-12-31 09:00
Actual Tiempo |  | 0.26736 | 1899-12-31 17:59
CPI (Cost-Performance Index) |  |  | 0.79
% Reuse | 68.2% | 69.6% | 34%
% New Reusable | 0% | 0% | 5.39%
Test Defects/KLOC or equivalent | 1.06 | 0 | 0.93
Total Defects/KLOC or equivalent | 20.1 | 7.63 | 18.6
Yield % | 84.2% | 100% | 85%
Code Review Rate | 888 | 655 | 978
% Appraisal COQ | 4.31% | 7.01% | 4.72%
% Failure COQ | 5.06% | 5.19% | 5.08%
COQ A/F Ratio | 0.85 | 1.35 | 0.93
PQI | 0.01 | 0.02 | 0.01
Program Size
| Plan | Actual | A la Fecha
Base (B) | 0 | 0 | 0
Deleted (D) | 0 | 0 | 0
Modified (M) | 0 | 0 | 0
Added (A) | 140 | 131 | 1076
Reused (R) | 300 | 300 | 408
Added and Modified (A+M) | 140 | 131 | 1076
Total Size (T) | 440 | 431 | 1200
Total New Reusable | 0 | 0 | 58
Estimated Proxy Size (E) | 127 | 131 | 560
Upper Prediction Interval (70%) | 210
Lower Prediction Interval (70%) | 70
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.040972 | 0.036111 | 0.26875 | 15.4%
DiseÃ±o | 0.019444 | 0.022222 | 0.13472 | 7.7%
RevisiÃ³n de DiseÃ±o | 0.0048611 | 0.010417 | 0.036806 | 2.1%
CodificaciÃ³n | 0.15486 | 0.14861 | 1899-12-31 00:47 | 59%
RevisiÃ³n de CodificaciÃ³n | 0.00625 | 0.0083333 | 0.045833 | 2.62%
CompilaciÃ³n | 0.0041667 | 0.0034722 | 0.025694 | 1.47%
Pruebas | 0.0090278 | 0.010417 | 0.063194 | 3.61%
Postmortem | 0.020139 | 0.027778 | 0.14167 | 8.1%
Total | 0.25903 | 0.26736 | 1899-12-31 17:59
Total Time UPI (70%) | 0.34514
Total Time LPI (70%) | 0.17361
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 0 | 0 | 0%
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0.89 | 0 | 6 | 30%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 1.92 | 1 | 14 | 70%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 2.81 | 1 | 20
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0 | 0 | 0 | 0%
RevisiÃ³n de DiseÃ±o | 0.15 | 0 | 1 | 5%
CodificaciÃ³n | 1.33 | 0 | 9 | 45%
RevisiÃ³n de CodificaciÃ³n | 0.89 | 1 | 7 | 35%
CompilaciÃ³n | 0.3 | 0 | 2 | 10%
Pruebas | 0.15 | 0 | 1 | 5%
Total | 2.81 | 1 | 20
After Development | 0 | 0 | 6
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 1.34 | 0 | 1.13
Defects/Hour - Code Review | 5.64 | 5 | 6.36
Defects/Hour - Compile | 3.17 | 0 | 3.24
Defects/Hour - Test | 0.67 | 0 | 0.66
DRL (DLDR/UT) | 2 | 0 | 1.72
DRL (Code Review/UT) | 8.44 | 7.58 | 9.65
DRL (Compile/UT) | 4.75 | 0 | 4.92
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 10:34 PM el 3/05/2017